## 00 · README + Launch Gate
Ascend / NewJob — Monetization QA & Publishing Workbook
Strict, engineering-clean rebuild of the Apero operating model. Tailored to the Ascend ad-arbitrage job app.
HOW TO USE
This workbook is the single source of truth for monetization + publishing QA. No build ships until it passes the Launch Gate below. Tabs flow: Checklist → Ad Script → Remote Config → Rewarded → IAP → Ad QA → Lifecycle QA → Event QA → Bug Log → Release History.
⚠ SECRET HYGIENE — READ FIRST
The original Apero sheets leaked live secrets: an Adjust key, a Facebook client token, a signing SHA fingerprint, AdMob app + ad-unit IDs, and Firebase console / APK links. DO NOT repeat that here. This workbook stores ad_unit_id and keys as PLACEHOLDERS only. Real values live in local.properties, CI secrets, Play/Firebase console, or 1Password — never in a shared sheet or Git.
★ MONETIZATION QA GATE (all must pass before PPC scale)
1 | Ad-script compliance — every live placement exists in the Ad Script tab with an owner, RC key, and cap.
2 | Remote Config compliance — every placement is RC-controlled; missing key defaults OFF for full-screen formats; no blank ad containers.
3 | Full-screen ad mutex — only ONE of {app-open, interstitial, rewarded, paywall, purchase dialog, permission dialog} can be on screen at once.
4 | Paid-user suppression — paid users see no forced ads, no native loading placeholders, no app-open; opt-in rewarded only.
5 | Rewarded correctness — reward granted ONLY on the earned-reward SDK callback, exactly once, never on ad close; no reward on fail/offline.
6 | Lifecycle / no-internet — ad failure never blocks the core loop; offline + reconnect handled per format.
7 | ILRD + IAP event logging — ad_impression (value+currency) and purchase fire correctly and are verified in GA4 DebugView.
8 | Release-build validation — verified on a production-signed AAB via Play Internal Testing, not just a debug build.
9 | Consent / policy compliance — privacy policy, Play Data Safety, UMP/consent behavior, Advertising-ID + ads declarations, app-ads.txt verified (see tab 12).
TIES TO ACQUISITION (why the gate matters)
tROAS for Ad Revenue (ARO) consumes ONLY the imported ad_impression event and only under the tROAS bid type. A logging gap (criteria 7) silently corrupts monetization, AdMob value-segmentation, AND Google Ads bidding at the same time. Fix measurement before scaling spend.
STATUS LEGEND
Pass = verified on release AAB · Fail = defect logged in Bug Log · Pending = not yet tested · Blocked = waiting on dep · N/A = not in this app version
PROCESS: delete the [SAMPLE] row in the Bug Log before active QA so counts stay accurate. Fill caps/product IDs/prices/geos before implementation freeze (see Launch Decisions, Rewarded Unlock Matrix, IAP + Subscription, and Consent + Policy QA).

## 00b · Launch Decisions
Launch Decisions — confirmed for handoff
Captured from product. These resolve the open questions; anything marked TODO still needs a value before scale.
Package | Brand-new package + app. Second copy of a validated idea. No conversion history yet.
Buying channel | Google App Campaigns ONLY. No third-party MMP. Attribution = Firebase/GA4 + Google Ads link.
Mediation owner | AdMob Mediation (sole control plane). Not running MAX as a parallel owner.
Ad sources | AdMob Network = WATERFALL backstop. Pangle, Mintegral, AppLovin, Liftoff Monetize = BIDDING.
Floors | Launch with AdMob ad-source optimization ON, no aggressive floors. After volume stabilizes, add PER-GEO price floors seeded from current app eCPM reference numbers.
Reference data | Reuse current app eCPM / retention / session benchmarks to seed expectations for the new copy.
Bidding ladder | tCPI (1–2 wks volume) → tCPA on onboarding_complete → tROAS-ARO/Hybrid after ~30d ad_impression value + ~50+ conv/mo. Do NOT start on tROAS.
Activation event | onboarding_complete (recommended tCPA event — early, high volume). core_action_done as the tighter alternative once volume allows.
Monetization control | Firebase Remote Config — controls ad placements/caps/tiers (NOT billing). Separate system from Play Billing.
Launch ad tier | ad_aggressiveness_tier = balanced at launch. → arbitrage_high per cheap geo after ~1 wk stable. → retention_protect for high-IAP geos.
Subscriptions | Google Play Billing (direct). No RevenueCat.
App Open ads | IN v1. Session 2+ if activated, else session 3. Suppression zones per Ad QA tab (OA01–OA12 + AX rules).
v1 scope | EVERYTHING shared is in v1: jobs, resume optimizer + builder, mock interview, copilot, tracker, games hub, ads, paywall.
Secrets owner | Fayyaz (PM) works with devs. All keys/IDs in console / local.properties / vault — never in these sheets or Git.
TODO — Fayyaz/you | Real Play product IDs + prices (IAP tab placeholders).
Free-tier model | RESOLVED: free users rewarded-gated (no free allowance) on resume download + cover letter + mock; Copilot is Pro-only (fully gated, no rewarded); paid users = ZERO ads entire journey. Caps in Rewarded tab, RC-adjustable.
TODO — Eng | Confirm each bidding adapter is integrated + ad-source optimization enabled in AdMob.
Launch geos | Worldwide incl. EEA/UK (CONFIRMED). All five networks relevant; Pangle/Mintegral carry more non-US inventory.
UMP / consent | HARD LAUNCH BLOCKER for EEA + UK + Switzerland only. Google-certified CMP (UMP/TCF) before personalized ads. UMP SDK ships globally but is region-gated. Brazil/SA = privacy-law review, NOT this gate. See tab 12.
Default RC tier | balanced at launch worldwide. arbitrage_high per cheap geo after ~1 wk stable; retention_protect for high-IAP geos.
TODO — Fayyaz/you | Final Play product IDs (currently NOT decided — IAP tab shows TBD).
TODO — Fayyaz/you | Final base prices for weekly / yearly / lifetime (+ yearly trial decision). LOCALIZED worldwide via Play pricing templates — purchase event sends real local value+currency (see IAP tab).

## 01 · Publishing Checklist
Publishing & SDK Checklist
Ascend-specific plumbing. Replace every credential cell with a 1Password/console reference — never the value itself.
No. | Element | Description / what "done" means | Owner | Status | Evidence (link/where) | Verify by | Verify status | Gate
0 | Release build (AAB) | Production-signed AAB uploaded to Play Internal Testing | Eng | Pending | [Play Console link] | Lead | Pending | Launch blocker
1 | Firebase project | GA4 + Firebase linked; Analytics enabled | Eng | Pending | [Firebase console — do not paste key] | Lead | Pending | Launch blocker
2 | google-services.json | Added to app module; package matches | Eng | Pending | in repo (not committed if it carries keys) | Lead | Pending | Launch blocker
3 | AdMob app + ad units | App ID + all ad-unit IDs mapped; IDs in local.properties only | Eng + Fayyaz | Pending | [1Password: Ascend AdMob] | Lead | Pending | Launch blocker
4 | Mediation (one owner) | AdMob Mediation = sole owner. AdMob Network as WATERFALL backstop; Pangle, Mintegral, AppLovin, Liftoff as BIDDING sources. Hybrid groups. | Eng | Pending | AdMob mediation groups | Lead | Pending | Launch blocker
5 | ILRD revenue listener | OnPaidEvent/paid listener on EVERY format; valueMicros→value normalized | Eng | Pending | MonetizationManager | Lead | Pending | Launch blocker
6 | Implement ads per Ad Script | Every placement matches tab "02 · Ad Script"; one placement_id per request | Eng | Pending | Ad Script tab | Lead | Pending | Launch blocker
7 | Remote Config | All keys from tab "03" published; missing-key defaults safe | Eng | Pending | Firebase Remote Config | Lead | Pending | Launch blocker
8 | ad_impression → GA4 | value+currency+params logged; verified in DebugView | Eng | Pending | GA4 DebugView | Lead | Pending | Launch blocker
9 | ad_impression imported to Google Ads | Imported as conversion; tROAS-ARO / Hybrid eligible | UA | Pending | Google Ads conversions | Lead | Pending | Scale blocker
10 | Play Billing (direct) | Products live; entitlement + restore tested | Eng | Pending | IAP tab | Lead | Pending | Launch blocker
11 | Crashlytics | Crash-free smoke test; PII filtered from logs | Eng | Pending | Crashlytics | Lead | Pending | Launch blocker
12 | FCM push | Channels created (jobs_fresh, tracker, resume_interview, winback, monetization) | Eng | Pending | FCM | Lead | Pending | Scale blocker
13 | Event logging | All events in tab "08" fire with required params | Eng | Pending | Event QA tab | Lead | Pending | Launch blocker
14 | Attribution SDK | GOOGLE APP CAMPAIGNS ONLY — no Adjust/AppsFlyer needed; Firebase/GA4 + Google Ads link is the attribution path. | — | N/A | — | Lead | Pending | Nice-to-have
15 | Google Ads ↔ Firebase link | Linked; real-time conversion sync on | UA | Pending | Google Ads linking | Lead | Pending | Scale blocker
16 | Privacy & Data Safety | Policy URL, Data Safety form, mic + resume/document disclosure, AI-content disclosure | Fayyaz (PM) | Pending | [Policy URL] | Lead | Pending | Launch blocker
17 | app-ads.txt | Published on store/developer domain; verified | PM | Pending | [domain]/app-ads.txt | Lead | Pending | Scale blocker
18 | Store listing | Icon, feature graphic, screenshots from REAL native app, copy | PM | Pending | Play Console listing | Lead | Pending | Launch blocker

## 02 · Ad Script
Ad Script — master placement contract
QA validates against this. Canonical snake_case IDs. ad_unit_id stays a placeholder; real IDs in local.properties.
placement_id | screen | trigger / when shown | ad_format | ad_unit_id (placeholder) | remote_config_key | frequency / cap | cooldown | first eligible | paid_user_behavior | no_fill_behavior | offline_behavior | mockup | qa_status | load_strategy | blocking_behavior
ad_native_language | Onboarding lang | After language list | Native | {native_language} | ads.native.language.enabled | 1 per screen | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_native_onboarding_final | End onboarding | After role+location, before Home | Native | {native_onb_final} | ads.native.onboarding_final.enabled | 1 | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_native_home_mid | Home | After Quick Actions | Native | {native_home} | ads.native.home.enabled | 1 per home view | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_native_job_list | Jobs results | After first 4 organic, then every N | Native | {native_job_list} | ads.native.job_list.enabled | every 6 (RC: frequency) | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_inter_after_search_batch | Jobs results | After 2–3 searches / Load more | Interstitial | {inter_search} | ads.inter.search_batch.enabled | max 1–2 / session | 90–180s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_inter_after_job_detail_close | Job detail | Close detail after viewing ≥2 | Interstitial | {inter_jobdetail} | ads.inter.job_detail_close.enabled | max 1–2 / session | 90–180s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_native_job_detail_bottom | Job detail | Below description | Native | {native_jobdetail} | ads.native.job_detail.enabled | 1 | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_rewarded_resume_optimize | Resume optimizer | Tap Apply AI fixes (after free score) | Rewarded | {rew_resume_opt} | ads.reward.resume_optimize.enabled | — | — | any | unlimited / no ad | retry/upgrade | retry/upgrade | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_rewarded_resume_download | Resume result | Tap Download optimized resume | Rewarded | {rew_resume_dl} | ads.reward.resume_download.enabled | — | — | any | unlimited / no ad | retry/upgrade | retry/upgrade | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_rewarded_cover_letter | Resume tools | Generate cover letter | Rewarded | {rew_cover} | ads.reward.cover_letter.enabled | — | — | any | unlimited / no ad | retry/upgrade | retry/upgrade | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_native_resume_result | Resume result | Below score, before suggestions | Native | {native_resume_res} | ads.native.resume_result.enabled | 1 | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_inter_after_resume_score | Resume result | Close result / finish optimize | Interstitial | {inter_resume} | ads.inter.resume_score.enabled | max 1 / session | 180s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_rewarded_mock_start | Mock setup | Start mock after free allowance | Rewarded | {rew_mock_start} | ads.reward.mock_start.enabled | — | — | any | unlimited / no ad | retry/upgrade | retry/upgrade | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_rewarded_mock_score | Mock report | Unlock detailed AI scoring | Rewarded | {rew_mock_score} | ads.reward.mock_score.enabled | — | — | any | unlimited / no ad | retry/upgrade | retry/upgrade | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_inter_after_mock_report | Mock report | Exit report (no rewarded <180s) | Interstitial | {inter_mock} | ads.inter.mock_report.enabled | max 1 / session | 180s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_rewarded_copilot_session | Copilot setup | Pro only — Copilot is fully gated behind paywall (NO rewarded unlock) | N/A — reserved | N/A | ads.reward.copilot_session.enabled | — | — | any | N/A — Pro feature (no ads) | N/A | retry/upgrade | [Figma] | N/A | N/A | N/A
ad_inter_after_copilot_end | Copilot ended | Tap Done (no rewarded just played) | Interstitial | {inter_copilot} | ads.inter.copilot_end.enabled | max 1 / session | 180s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_native_tracker_empty | Tracker (empty) | No tracked jobs | Native | {native_tracker} | ads.native.tracker_empty.enabled | 1 | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_native_games_hub | Games hub | After first game row | Native | {native_games} | ads.native.games_hub.enabled | 1 | — | session 1 | hidden | collapse | hide | [Figma] | Pending | lazy | non-blocking collapse
ad_inter_after_game_complete | Game complete | After completion | Interstitial | {inter_game} | ads.inter.game_complete.enabled | 1 per 2 games | 90s | session 2 | suppress | — | skip | [Figma] | Pending | preload | fail open
ad_rewarded_game_hint | Game | Hint / redo / extra puzzle | Rewarded | {rew_game_hint} | ads.reward.game_hint.enabled | — | — | any | no ad (free for Pro) | retry | retry | [Figma] | Pending | on-demand | gated; clear retry/upgrade
ad_appopen_resume | App resume | Return from background | App-open | {appopen_resume} | ads.appopen.resume.enabled | 1/sess · 2/day | 30 min | s2 if activated, else s3 | suppress | — | skip | [Figma] | Pending | preload | fail open

## 03 · Remote Config Matrix
Remote Config Matrix — no blanks allowed
Every full-screen placement defaults OFF on a missing key. This is the control plane the strategy doc references.
remote_key | default_value | allowed_values | owner | screen / scope | placement_id | paid_user_behavior | offline_behavior | missing_key_behavior | qa_status
ad_aggressiveness_tier | balanced | retention_protect¦balanced¦arbitrage_high¦paid_or_high_intent | PM | global | — | paid_or_high_intent | last cached | balanced | Pending
ads_global_enabled | true | true¦false | PM | global | all | n/a | respect cache | false | Pending
ads.native.job_list.enabled | true | true¦false | PM | Jobs | ad_native_job_list | hidden | hide | false | Pending
ads.native.job_list.frequency | 6 | 4¦6¦8 | PM | Jobs | ad_native_job_list | n/a | n/a | 8 | Pending
ads.native.home.enabled | true | true¦false | PM | Home | ad_native_home_mid | hidden | hide | false | Pending
ads.native.resume_result.enabled | true | true¦false | PM | Resume | ad_native_resume_result | hidden | hide | false | Pending
ads.inter.search_batch.enabled | false | true¦false | PM | Jobs | ad_inter_after_search_batch | suppress | skip | false | Pending
ads.inter.job_detail_close.enabled | false | true¦false | PM | Job detail | ad_inter_after_job_detail_close | suppress | skip | false | Pending
ads.inter.resume_score.enabled | false | true¦false | PM | Resume | ad_inter_after_resume_score | suppress | skip | false | Pending
ads.inter.mock_report.enabled | false | true¦false | PM | Mock | ad_inter_after_mock_report | suppress | skip | false | Pending
ads.inter.cooldown_seconds | 120 | 60–300 | PM | global | all interstitial | n/a | n/a | 180 | Pending
ads.inter.max_per_session | 2 | 1¦2¦3 | PM | global | all interstitial | 0 | n/a | 1 | Pending
ads.reward.resume_optimize.enabled | true | true¦false | PM | Resume | ad_rewarded_resume_optimize | opt-in only | retry/upgrade | false | Pending
ads.reward.mock_score.enabled | true | true¦false | PM | Mock | ad_rewarded_mock_score | opt-in only | retry/upgrade | false | Pending
ads.reward.daily_cap | 5 | 3–8 | PM | global | all rewarded | n/a | n/a | 3 | Pending
ads.appopen.resume.enabled | true | true¦false | PM | App resume | ad_appopen_resume | OFF | skip | false | Pending
ads.appopen.resume.min_session | 2 | 2¦3¦4 | PM | App resume | ad_appopen_resume | n/a | n/a | 3 | Pending
ads.appopen.resume.require_activation_for_session_2 | true | true¦false | PM | App resume | ad_appopen_resume | n/a | n/a | true | Pending
ads.appopen.resume.cooldown_minutes | 30 | 20–60 | PM | App resume | ad_appopen_resume | n/a | n/a | 45 | Pending
ads.appopen.resume.max_per_session | 1 | 1 | PM | App resume | ad_appopen_resume | 0 | n/a | 1 | Pending
ads.appopen.resume.max_per_day | 2 | 1¦2¦3 | PM | App resume | ad_appopen_resume | 0 | n/a | 2 | Pending
ads.appopen.resume.suppress_after_fullscreen_ad_seconds | 180 | 120–300 | PM | App resume | ad_appopen_resume | n/a | n/a | 300 | Pending
ads.appopen.resume.load_timeout_ms | 1200 | 800–1500 | PM | App resume | ad_appopen_resume | n/a | n/a | 1200 | Pending
ads.appopen.resume.ad_expiration_hours | 4 | 4 | Eng | App resume | ad_appopen_resume | n/a | n/a | 4 | Pending
paywall.variant | control | control¦discount¦trial¦lifetime | PM | Paywall | — | n/a | last cached | control | Pending
paywall.suppress_if_rewarded_engaged | true | true¦false | PM | Paywall | — | n/a | n/a | true | Pending
push.jobs_fresh.daily_cap | 1 | 0–2 | PM | push | — | n/a | n/a | 1 | Pending
push.winback.enabled | true | true¦false | PM | push | — | n/a | n/a | false | Pending
ads.appopen.resume.min_background_seconds | 30 | 15-60 | Eng | App resume | ad_appopen_resume | n/a | n/a | 30 | Pending
ads.appopen.resume.suppress_after_external_link_seconds | 300 | 120-600 | PM | App resume | ad_appopen_resume | n/a | n/a | 300 | Pending
ads.appopen.resume.suppress_after_rewarded_seconds | 300 | 120-600 | PM | App resume | ad_appopen_resume | n/a | n/a | 300 | Pending
ads.appopen.resume.suppress_after_permission_seconds | 120 | 60-300 | PM | App resume | ad_appopen_resume | n/a | n/a | 120 | Pending
ads.appopen.resume.suppress_during_resume_flow | true | true¦false | PM | Resume | ad_appopen_resume | n/a | n/a | true | Pending
ads.appopen.resume.suppress_during_mock_flow | true | true¦false | PM | Mock | ad_appopen_resume | n/a | n/a | true | Pending
ads.appopen.resume.suppress_during_copilot_flow | true | true¦false | PM | Copilot | ad_appopen_resume | n/a | n/a | true | Pending
ads.appopen.resume.suppress_during_billing_flow | true | true¦false | PM | Billing | ad_appopen_resume | n/a | n/a | true | Pending
ads.fullscreen.mutex_enabled | true | true¦false | Eng | global | all fullscreen | n/a | n/a | true | Pending
ads.suppress_for_paid_users | true | true¦false | Eng | global | all | n/a | n/a | true | Pending
ads.inter.load_timeout_ms | 1000 | 800-1200 | Eng | global | all interstitial | n/a | skip | 1000 | Pending
ads.reward.load_timeout_ms | 4000 | 3000-5000 | Eng | global | all rewarded | n/a | retry | 4000 | Pending
ads.native.load_timeout_ms | 0 | non-blocking | Eng | global | all native | n/a | collapse | 0 | Pending
ads.reward.copilot_session.enabled | false | true¦false | PM | Copilot | ad_rewarded_copilot_session | Pro only | n/a | false | Pending
ads.native.language.enabled | true | true¦false | PM | Onboarding lang | ad_native_language | hidden | hide | false | Pending
ads.native.onboarding_final.enabled | true | true¦false | PM | End onboarding | ad_native_onboarding_final | hidden | hide | false | Pending
ads.native.job_detail.enabled | true | true¦false | PM | Job detail | ad_native_job_detail_bottom | hidden | hide | false | Pending
ads.native.tracker_empty.enabled | true | true¦false | PM | Tracker | ad_native_tracker_empty | hidden | hide | false | Pending
ads.native.games_hub.enabled | true | true¦false | PM | Games hub | ad_native_games_hub | hidden | hide | false | Pending
ads.inter.copilot_end.enabled | false | true¦false | PM | Copilot ended | ad_inter_after_copilot_end | suppress | skip | false | Pending
ads.inter.game_complete.enabled | false | true¦false | PM | Game complete | ad_inter_after_game_complete | suppress | skip | false | Pending
ads.reward.resume_download.enabled | true | true¦false | PM | Resume result | ad_rewarded_resume_download | opt-in only | retry/upgrade | false | Pending
ads.reward.cover_letter.enabled | true | true¦false | PM | Resume tools | ad_rewarded_cover_letter | opt-in only | retry/upgrade | false | Pending
ads.reward.mock_start.enabled | true | true¦false | PM | Mock setup | ad_rewarded_mock_start | opt-in only | retry/upgrade | false | Pending
ads.reward.game_hint.enabled | true | true¦false | PM | Game | ad_rewarded_game_hint | opt-in only | retry | false | Pending

## 04 · Rewarded Unlock Matrix
Rewarded Unlock Matrix
Reward fires ONLY on the earned-reward SDK callback, exactly once. Never on ad close. Never on fail/offline.
placement_id | trigger | reward (exact, concrete) | grant rule | free cap | paid behavior | fallback if ad fails / no-fill | free_daily_cap | rewarded_daily_cap | reset_window | server_verified
ad_rewarded_resume_optimize | Apply AI fixes (after free score shown) | Optimize this resume once | on OnUserEarnedReward → unlock once | rewarded only | unlimited, no ad | show "Ad unavailable — try again or upgrade" · score free; apply/download via rewarded | 0 | 3 | 24h | backend+local
ad_rewarded_resume_download | Download optimized resume | One export/download | on earned-reward callback | rewarded only | unlimited, no ad | paywall first, rewarded after dismiss | 0 | 3 | 24h | backend+local
ad_rewarded_cover_letter | Generate cover letter | One cover letter for this job | on earned-reward callback | rewarded only | unlimited, no ad | retry / upgrade | 0 | 5 | 24h | backend+local
ad_rewarded_mock_start | Start mock after free allowance | One mock interview session | on earned-reward callback | 1/day free, then rewarded | unlimited, no ad | retry / upgrade | 1 | 3 | 24h | backend+local
ad_rewarded_mock_score | Unlock detailed AI scoring | Full score + improvement tips | on earned-reward callback | rewarded only | unlimited, no ad | retry / upgrade | 0 | 3 | 24h | backend+local
ad_rewarded_copilot_session | Start copilot session | RESERVED PLACEHOLDER — do NOT implement. Copilot is Pro-only (paywall). | No rewarded path | rewarded only | Included in Pro; no rewarded path | Copilot = Pro feature only; see IAP/paywall | PRO ONLY | n/a | n/a | backend+local
ad_rewarded_game_hint | Request hint / extra puzzle | One hint or extra game | on earned-reward callback | daily cap | no ad (free for Pro) | retry | 1 | 5 | 24h | backend+local

## 05 · IAP + Subscription
IAP / Subscription + Ad-Suppression Matrix
Products are placeholders. Entitlement caching + restore are mandatory QA. Tie every paid state to ad behavior.
product_id | type | base price + localization | trial | entitlement key | free vs Pro gate | restore tested
ascend.weekly [TBD — not finalized] | weekly | Base USD [TBD] → Play localized pricing (auto-FX or custom per market) | optional | pro | Pro = no forced ads + unlimited resume/mock/cover | Pending
ascend.yearly [TBD — not finalized] | yearly | Base USD [TBD] → Play localized pricing (auto-FX or custom per market) | yearly-trial | pro | Pro = no forced ads + unlimited | Pending
ascend.lifetime [TBD — not finalized] | lifetime | Base USD [TBD] → Play localized pricing (auto-FX or custom per market) | — | pro_lifetime | Pro = no forced ads + unlimited | Pending
Subscription × Ad QA matrix
user state | native | interstitial | app-open | rewarded | billing / reward | expected
Free | per RC | per RC | per RC | per RC | — | ads per tier/segment
Paid (active) | hidden | OFF | OFF | opt-in only | — | no forced ads, no loading placeholders
Expired | per RC | per RC | per RC | per RC | — | reverts to free ad behavior
Purchase pending | hidden | OFF | OFF | — | no dup billing | no reward until confirmed
Purchase canceled | per RC | per RC | per RC | per RC | — | stays on prior screen cleanly
Cache cleared | hidden | OFF | OFF | opt-in | restore | entitlement restored correctly
Offline (was paid) | hidden | OFF | OFF | opt-in | — | entitlement cache respected
Play Billing failure / edge states (add to ad-suppression QA)
state | expected behavior | ads | reward | notes | status | owner
Billing unavailable | Hide Pro CTAs gracefully; app still usable | per RC | — | Play services missing/old | Pending | Eng
Purchase failed | Stay on screen; clear error; no entitlement | per RC | — | network/declined | Pending | Eng
Purchase deferred/pending | No entitlement, no reward until resolved | suppress | no reward | slow/3rd-party payment | Pending | Eng
Restore failed | Treat as free + visible "Restore" option | per RC | — | offline/no record | Pending | Eng
Refunded / revoked | Drop entitlement; revert to free ad behavior | per RC | — | Play revoke webhook/recheck | Pending | Eng
Grace period | Keep Pro (no forced ads) during grace | suppress | — | payment retry window | Pending | Eng
Account hold | Revert to free until payment fixed | per RC | — | hold state | Pending | Eng
Product not found | Fail safe; hide that product; log | per RC | — | SKU mismatch | Pending | Eng
Duplicate purchase attempt | Block double charge; acknowledge once | suppress | — | already owned | Pending | Eng
entitlement_unknown | Do NOT show forced ads until restore resolves; use cache; if offline+no cache treat as free w/ restore | suppress | suppress | the cache-cleared gap | Pending | Eng
NOTE: ascend.lifetime = one-time in-app product (does NOT renew). weekly/yearly = subscriptions. Do not implement lifetime as a subscription.
Localized pricing — implementation rules (worldwide incl. EEA/UK)
• Set base price per product in Play Console; use Play pricing templates so all markets stay in sync. Auto-converted by default; override per market where needed (psychological price points, tax-inclusive EU display).
• PURCHASE EVENT MUST send the REAL local price + ISO currency from Play Billing ProductDetails of that transaction. NEVER hardcode USD. A ₹/R$/€ sale must report its own value+currency.
• GA4 converts incoming revenue to the property reporting currency for dashboards; Google Ads converts to account currency for tROAS. You send local; Google handles FX. Do not pre-convert client-side.
• EU/EEA: prices shown tax-inclusive; Play handles VAT. Confirm displayed price matches Play confirmation sheet (Apero QA: trial/price text must match).
• QA: verify purchase value+currency in GA4 DebugView for at least 2 non-USD test markets before scale.

## 06 · Ad QA Test Cases
Ad QA Test Cases
Ported from Apero IA/OA/N/B/R taxonomy + Ascend-specific cases. Dual sign-off: partner check then QA(QC) confirm.
Pass | 0
Fail | 0
Pending | 48
TC ID | format | test | expected result | partner check | QA (QC) confirm | priority | tester | notes | evidence_link | build_version | device | date
1 · Interstitial
IA01 | Interstitial | Loading ad shown before full ad | Loading state, then interstitial |  | Pending | Medium
IA02 | Interstitial | Click ad | Redirects to landing page |  | Pending | Medium
IA03 | Interstitial | Close ad | Next screen shown immediately |  | Pending | High
IA04 | Interstitial | Two full-screen ads conflict | MUTEX: only one full-screen ad at a time |  | Pending | Critical
IA05 | Interstitial | Show after splash loads | No ad before splash; loading then ad |  | Pending | High
IA06 | Interstitial | No internet | Flow continues normally; no block |  | Pending | High
IA07 | Interstitial | Ad does not overlay app content/audio | No popup/music overlap during ad |  | Pending | Medium
2 · App-open / Resume
OA01 | App-open | Background fill under resume ad | Branded/neutral surface, no half-rendered content |  | Pending | Medium
OA02 | App-open | Click resume ad | Redirects to landing page |  | Pending | Medium
OA03 | App-open | Close resume ad | Returns to the resume screen |  | Pending | High
OA04 | App-open | Return from permission/settings | Do NOT show resume ad |  | Pending | High
OA05 | App-open | On IAP/Sub, Terms, Privacy screens | Do NOT show resume ad |  | Pending | High
OA06 | App-open | Return from Rate-Us / share sheet | Do NOT show resume ad |  | Pending | Medium
OA07 | App-open | No internet on resume | No ad; functions work normally |  | Pending | High
OA08 | App-open | Not first launch | No app-open on session 1; s2 only if activated |  | Pending | Critical |  | Ascend rule
OA09 | App-open | Return from external apply link | Do NOT show; show tracker prompt instead |  | Pending | High |  | Ascend rule
OA10 | App-open | During resume upload / mock / copilot | Do NOT show app-open |  | Pending | Critical |  | Ascend rule
3 · Native
N01 | Native | Loading placeholder before ad | Placeholder same size as final ad |  | Pending | Medium
N02 | Native | Layout | Not overlapped or cut |  | Pending | Medium
N03 | Native | Background differs from app bg | Distinguishable |  | Pending | Low
N04 | Native | AdChoices | Inside the ad frame |  | Pending | Medium
N05 | Native | "AD" label | Visible, stands out |  | Pending | High
N06 | Native | MediaView | Min 120x120dp |  | Pending | Medium
N07 | Native | Title truncation | Ellipsize cleanly (Apero ref: ~25 chars; test long strings — do not hardcode) |  | Pending | Medium
N08 | Native | Body truncation | Ellipsize cleanly (Apero ref: ~90 chars; test long strings) |  | Pending | Medium
N09 | Native | Does not cover app content | No overlap either direction |  | Pending | Medium
N10 | Native | Click ad | Links to landing page |  | Pending | Medium
N11 | Native | No internet / no-fill | Hide loading + ad cleanly; container collapses |  | Pending | High
N12 | Native | Job-list ad labeled | Looks like a card but clearly "Sponsored/Ad" |  | Pending | High |  | Ascend rule
4 · Banner (only if a placement proves profitable)
B01 | Banner | Loading before ad | Loading then banner |  | N/A | Low |  | N/A until a banner placement is added to Ad Script
B02 | Banner | Does not cover content | Anchored, no overlap |  | N/A | Low |  | N/A until a banner placement is added to Ad Script
B03 | Banner | Click | Links to landing page |  | N/A | Low |  | N/A until a banner placement is added to Ad Script
B04 | Banner | No internet | Hide cleanly |  | N/A | Low |  | N/A until a banner placement is added to Ad Script
5 · Rewarded
R01 | Rewarded | Reward sign at trigger | Clear "watch ad to..." with exact reward |  | Pending | High
R02 | Rewarded | Click ad | Links to landing page |  | Pending | Medium
R03 | Rewarded | Complete ad | Reward granted on earned-reward callback, ONCE |  | Pending | Critical
R04 | Rewarded | Two full-screen ads conflict | MUTEX honored |  | Pending | Critical
R05 | Rewarded | No internet | Clear message; NO reward |  | Pending | High
R06 | Rewarded | Close early / ad fails | NO reward; retry/upgrade fallback |  | Pending | Critical
R07 | Rewarded | No interstitial stacked after rewarded | Suppress interstitial ≥180s after rewarded |  | Pending | High |  | Ascend rule
6 · Ascend value-protection (no ad at the wrong moment)
AX01 | All | No ad before first value moment (session 1) | No FULL-SCREEN ad before first value (session 1). Native is allowed only if it does not block onboarding, does not shift layout, and collapses on no-fill. |  | Pending | Critical
AX02 | All | No ad during resume upload/parsing | Clean flow |  | Pending | Critical
AX03 | All | No ad during active mock interview | Clean flow |  | Pending | Critical
AX04 | All | No ad during active copilot session | Clean flow |  | Pending | Critical
AX05 | All | No forced ad for paid users | Suppressed everywhere |  | Pending | Critical
AX06 | All | Remote key OFF hides placement | No blank container remains |  | Pending | High
AX07 | All | No infinite ad loading | Fail open after timeout |  | Pending | Critical
OA11 | App-open | Return from ad landing page | Do NOT show app-open |  | Pending | High |  | Ascend rule
OA12 | App-open | Foreground after <30s background | Do NOT show app-open |  | Pending | High
N13 | Native | Paid-user suppression | No native loading placeholder remains for paid users |  | Pending | Critical
R08 | Rewarded | Double-tap / duplicate reward | Reward granted exactly once, never twice |  | Pending | Critical
AX08 | All | No ad requested before UMP consent resolves | Ad SDK init / first request gated behind canRequestAds()==true; EEA/UK/CH form shown first |  | Pending | Critical |  | EEA/UK/CH

## 07 · Lifecycle + No-Internet
Lifecycle / No-Internet / Reconnect QA
Rule: an ad failure must NEVER block the core loop. Rewarded is the only gated exception, and still needs a clear state.
# | scenario | expected | status | notes
1 | Start app offline | App opens; search shows offline/empty state | Pending
2 | Search jobs offline | Clear offline state; no stuck loader | Pending
3 | Open saved jobs / tracker offline | Local Room data shows | Pending
4 | Start resume optimizer offline | Clear message; no infinite load | Pending
5 | Lose internet during rewarded ad | No reward; retry/upgrade message | Pending
6 | Reconnect while ad loading | Recovers or fails open; flow continues | Pending
7 | Reconnect after failed search | Search works; no duplicate calls | Pending
8 | Reconnect after failed resume upload | Upload ret[ries] cleanly | Pending
9 | Interstitial not ready at trigger | Continue immediately; preload next | Pending
10 | App backgrounded <15–30s then resumed | No app-open ad | Pending
11 | Two full-screen triggers race | Mutex: second is suppressed | Pending
12 | Push tap into active flow | No app-open over the flow | Pending
13 | App killed/restarted while ad was loaded | No stale ad shown; reload cleanly | Pending
14 | App killed/restarted during rewarded unlock | No reward unless earned-callback fired; safe state | Pending
15 | Resume after returning from Play Billing | No app-open ad over billing return | Pending
16 | Resume after file picker | No app-open ad over picker return | Pending
17 | Resume after microphone permission | No app-open ad over permission return | Pending

## 08 · Event Tracking QA
Event Tracking QA — execution tracker (mirrors Event Schema contract)
ad_impression is the keystone (tROAS-ARO). Verify value+currency in DebugView, Realtime, and BigQuery. Event names match the schema 1:1.
event | feeds | required params | Implemented? | DebugView | BigQuery | GAds imported | owner | priority | status
Acquisition & Activation
first_open | attribution | referrer_source, install_id | Pending | Pending | Pending | N/A |  | P0 | Pending
onboarding_step | funnel | step, skipped | Pending | Pending | Pending | N/A |  | P2 | Pending
onboarding_complete | activation | target_role_present, target_role_category, location_type, resume_uploaded | Pending | Pending | Pending | N/A |  | P0 | Pending
core_action_done | activation | action_type, session_number | Pending | Pending | Pending | N/A |  | P0 | Pending
Core Job Loop
job_search | behavior | query_present, filters_used, results_count, source | Pending | Pending | Pending | N/A |  | P1 | Pending
job_detail_view | behavior | match_score_band, employment_type, remote_type | Pending | Pending | Pending | N/A |  | P1 | Pending
job_save | intent | from_screen | Pending | Pending | Pending | N/A |  | P1 | Pending
job_apply_click | intent | apply_type | Pending | Pending | Pending | N/A |  | P1 | Pending
tracker_stage_change | intent | from_stage, to_stage | Pending | Pending | Pending | N/A |  | P2 | Pending
Resume & Interview
resume_upload | intent | file_type, file_size_band | Pending | Pending | Pending | N/A |  | P1 | Pending
resume_optimize_start | intent | has_target_job | Pending | Pending | Pending | N/A |  | P2 | Pending
resume_optimize_complete | quality | score_band, gated_by | Pending | Pending | Pending | N/A |  | P1 | Pending
resume_download | intent | format, gated_by | Pending | Pending | Pending | N/A |  | P2 | Pending
cover_letter_generate | quality | gated_by | Pending | Pending | Pending | N/A |  | P2 | Pending
mock_interview_start | behavior | gated_by, role_source | Pending | Pending | Pending | N/A |  | P2 | Pending
mock_interview_complete | quality | questions_answered, gated_by | Pending | Pending | Pending | N/A |  | P1 | Pending
copilot_session_start | behavior | gated_by | Pending | Pending | Pending | N/A |  | P2 | Pending
★ Monetization Spine — value+currency REQUIRED
ad_impression | BIDDING | value, currency, ad_format, ad_source, ad_unit, placement, precision, session_number | Pending | Pending | Pending | Pending |  | P0 | Pending
rewarded_ad_start | monetization | placement, reward_type | Pending | Pending | Pending | N/A |  | P1 | Pending
rewarded_ad_complete | monetization | reward_type, placement, reward_granted | Pending | Pending | Pending | N/A |  | P0 | Pending
purchase | BIDDING / IAP | value, currency, product_id, product_type, trial, is_renewal, transaction_id, purchase_source | Pending | Pending | Pending | Pending |  | P0 | Pending
Paywall
paywall_view | funnel | variant, trigger_placement | Pending | Pending | Pending | N/A |  | P1 | Pending
paywall_start_trial_click | funnel | variant | Pending | Pending | Pending | N/A |  | P1 | Pending
paywall_dismiss | funnel | variant | Pending | Pending | Pending | N/A |  | P2 | Pending
Retention & Push
session_start_enriched | segmentation | session_number, user_ad_segment, rc_variant, ad_aggressiveness_tier | Pending | Pending | Pending | N/A |  | P1 | Pending
app_open_resume | retention | was_ad_shown, suppressed_reason | Pending | Pending | Pending | N/A |  | P1 | Pending
push_sent | retention | channel (server-side) | Pending | Pending | Pending | N/A |  | P2 | Pending
push_open | retention | channel, deep_link_target | Pending | Pending | Pending | N/A |  | P1 | Pending
Failures & Errors (debug launch; separate "broke" from "lost interest")
job_search_failed | error | error_type | Pending | Pending | Pending | N/A |  | P1 | Pending
resume_upload_failed | error | error_type | Pending | Pending | Pending | N/A |  | P1 | Pending
resume_optimize_failed | error | error_type | Pending | Pending | Pending | N/A |  | P1 | Pending
mock_interview_failed | error | error_type | Pending | Pending | Pending | N/A |  | P2 | Pending
copilot_answer_failed | error | error_type | Pending | Pending | Pending | N/A |  | P2 | Pending
external_apply_failed | error | error_type | Pending | Pending | Pending | N/A |  | P2 | Pending
file_picker_cancelled | behavior | reason | Pending | Pending | Pending | N/A |  | P2 | Pending
permission_result | error | permission, granted | Pending | Pending | Pending | N/A |  | P1 | Pending
Ad Lifecycle Diagnostics (DEBUG — do NOT import to Google Ads as conversions)
ad_request | debug | placement_id, ad_format | Pending | Pending | N/A | N/A |  | P2 | Pending
ad_loaded | debug | placement_id, ad_format, ad_source | Pending | Pending | N/A | N/A |  | P2 | Pending
ad_load_failed | debug | placement_id, ad_format, reason | Pending | Pending | N/A | N/A |  | P1 | Pending
ad_show_attempt | debug | placement_id, ad_format | Pending | Pending | N/A | N/A |  | P2 | Pending
ad_show_failed | debug | placement_id, reason | Pending | Pending | N/A | N/A |  | P1 | Pending
ad_suppressed | debug | placement_id, reason (mutex/paid/cooldown/segment) | Pending | Pending | N/A | N/A |  | P1 | Pending
ad_dismissed | debug | placement_id, ad_format | Pending | Pending | N/A | N/A |  | P2 | Pending
Screens & Rewarded Diagnostics
screen_view | behavior | screen_name, screen_class (home/jobs/job_detail/tracker/resume/resume_result/mock_interview/copilot/games/paywall) | Pending | Pending | N/A | N/A |  | P1 | Pending
ad_reward_earned | debug | placement, reward_type — SDK says user EARNED reward | Pending | Pending | N/A | N/A |  | P0 | Pending
ad_reward_granted | debug | placement, reward_type — app ACTUALLY unlocked the feature (earned w/o granted = bug) | Pending | Pending | N/A | N/A |  | P0 | Pending

## 09 · Bug Log
Bug Log
English, single schema. Evidence link required. Status drives the rollup. Reopen until QC confirms.
Critical | 0
High | 0
N° | feature | actual result | description / video link | device | expected result | status | priority | tester | date | dev feedback | QC confirm | build_version | build_type | track | rc_variant | ad_tier | placement_id | evidence_link

## 10 · Release History
Release History
No release without the 9-point Monetization QA Gate passed on a production-signed AAB.
version | date | build type | track | QA gate passed | notes / changes | AAB versionCode | RC version | ad_script version | event_schema version | QA owner | approver

## 11 · Mediation Adapter QA
Mediation Adapter QA
Per-network readiness. You can pass placement QA while an adapter is half-wired — this tab prevents that. AdMob Mediation is sole owner.
ad_source | source_type | intended_formats | adapter_integrated | adapter_version | ad_source_optimization | test_ad_received | live_ad_received | ILRD_source_verified | no_fill_verified | geo group | evidence | owner | status | verified_in_admob_ui
AdMob Network | waterfall | native/inter/rewarded/app_open/banner | Pending | [ver] | ON | Pending | Pending | Pending | Pending | all | [link] | Eng | Pending | Pending
Pangle | bidding | native/inter/rewarded/app_open | Pending | [ver] | n/a (bidding) | Pending | Pending | Pending | Pending | all | [link] | Eng | Pending | Pending
Mintegral | bidding | native/inter/rewarded/app_open | Pending | [ver] | n/a (bidding) | Pending | Pending | Pending | Pending | all | [link] | Eng | Pending | Pending
AppLovin | bidding | native/inter/rewarded | Pending | [ver] | n/a (bidding) | Pending | Pending | Pending | Pending | all | [link] | Eng | Pending | Pending
Liftoff Monetize | bidding | inter/rewarded | Pending | [ver] | n/a (bidding) | Pending | Pending | Pending | Pending | all | [link] | Eng | Pending | Pending

## 12 · Consent + Policy QA
Consent + Policy QA
Resumes + microphone + ads + analytics all need clean disclosure even with no login. Most are launch blockers.
item | requirement | gate | owner | evidence / link | status
Privacy policy URL live | Reachable public URL; linked in app + store | Launch blocker | Fayyaz | [link] | Pending
Terms of use URL live | Reachable public URL | Launch blocker | Fayyaz | [link] | Pending
Play Data Safety form | Completed + accurate (resume files, audio, ad data) | Launch blocker | Fayyaz | [link] | Pending
Ads declaration | "Contains ads" declared in Play Console | Launch blocker | Fayyaz | [link] | Pending
Advertising ID permission | com.google.android.gms.permission.AD_ID declared (Android 13+) | Launch blocker | Fayyaz | [link] | Pending
app-ads.txt | Published on developer domain; verified in Play | Scale blocker | Fayyaz | [link] | Pending
UMP / Google-certified CMP | Required for EEA + UK + Switzerland before serving PERSONALIZED ads (IAB TCF). Ship the UMP SDK GLOBALLY; it decides per region whether to show the form. Brazil/South Africa are NOT under this certified-CMP mandate. | Launch blocker | Fayyaz | [link] | Pending
EEA / UK / Switzerland consent (GDPR/TCF) | Consent gathered via certified CMP before personalized ads in EEA/UK/CH. canRequestAds() stays false until consent info update runs. | Launch blocker | Fayyaz | [link] | Pending
US state privacy | US state laws (CCPA etc.) — handle via privacy options / Google settings. Separate from EEA TCF consent; NOT a certified-CMP gate. | Scale blocker | Fayyaz | [link] | Pending
Target audience / children | Declared NOT child-directed; no neg. targeting of minors | Launch blocker | Fayyaz | [link] | Pending
Microphone disclosure | In-app + store disclosure for copilot/mock audio | Launch blocker | Fayyaz | [link] | Pending
Resume/document disclosure | Disclose resume upload + AI processing + retention | Launch blocker | Fayyaz | [link] | Pending
AI-generated content disclosure | Disclose resume/cover/interview content is AI-assisted | Launch blocker | Fayyaz | [link] | Pending
Data deletion / support route | Working contact + deletion request path | Launch blocker | Fayyaz | [link] | Pending
Pre-launch report | Reviewed Play pre-launch report (crashes, policy, perf) | Launch blocker | Fayyaz | [link] | Pending
Launch geos confirmed | Determines UMP/GDPR + US-state privacy urgency (US-only vs worldwide vs EEA/UK) | Launch blocker | Fayyaz | Worldwide incl. EEA/UK — CONFIRMED | Pending
Brazil — LGPD | Privacy policy + lawful data handling (resume/audio/ads). NOT the EEA certified-CMP/TCF gate. Required only if launching in BR. | Launch blocker | Fayyaz | [link] | Pending
South Africa — POPIA | Privacy policy + lawful data handling. NOT the EEA certified-CMP/TCF gate. Required only if launching in ZA. | Launch blocker | Fayyaz | [link] | Pending
UMP implementation behavior (region-gated, globally shipped)
• On EVERY app launch: call requestConsentInfoUpdate() to check if consent is required + if a privacy-options entry is needed.
• canRequestAds() stays FALSE until the consent info update has run — do NOT request/initialize ads before it resolves.
• Call loadAndShowConsentFormIfRequired() — the form shows ONLY where required (EEA/UK/CH). Elsewhere it no-ops and ads proceed.
• If privacy options are required, add a persistent "Privacy options" entry in Settings.
• Gate ad SDK init / first ad request behind canRequestAds() == true. This is an ad-init rule, not just a legal checkbox.